## Sample Template for Option 2
Test Case ID | Application Feature Tested | Input | Expected output | Actual output | Status | Assumption for Expected Output
Neg_0001 | PDF editing | Open a password-protected PDF inside the PDF editor without entering the password. | The editor should either prompt for the password or display a message stating the file is locked. | The editor failed to load the file but did not prompt for a password or describe the cause. | Fail | It is assumed that locked PDFs should trigger a clear password prompt or an explanatory message.
Neg_0002 | PDF editing | Rename a PNG image to document.pdf (only the extension is changed) and try to open it in the PDF editor. | The editor should validate the file's actual content and refuse it with a message that the file is not a valid PDF document. | The editor accepted the file based on its extension, attempted to load it and produced a blank workspace with no error explanation. | Fail | It is assumed that the editor should verify the internal structure of the uploaded file rather than relying solely on the file extension.
Pos_0001 | PDF editing | Open a 3-page PDF, add a text annotation on page 1, and save the changes. | The annotated text should remain visible in the preview and persist in the saved file. | The annotation was placed correctly on page 1 and was retained in the saved output. | Pass | NA
Neg_0003 | Document conversion | Click the convert button without uploading any file into the document converter. | The conversion should not start and a message should prompt the user to upload a document first. | The convert button responded to the click but no message appeared and the page remained on the upload screen. | Fail | It is assumed that triggering the conversion without a file should produce a clear prompt instructing the user to upload a document.
Neg_0004 | Document conversion | Upload a Word document (.docx) whose file extension has been manually changed to .pdf, then attempt the conversion. | The converter should inspect the file's internal structure, detect the mismatch with the .pdf extension, and reject it with an appropriate message. | The converter trusted the extension, began processing the file as a PDF, and produced a corrupted output without any warning. | Fail | It is assumed that the converter should validate file contents against the declared format rather than relying on the file extension alone.
Pos_0002 | Document conversion | Upload a valid Microsoft Word file (.docx, ~50 KB) and convert it to PDF. | A converted PDF should be produced and a download button should appear once conversion completes. | The PDF was generated successfully and a download option was shown to the user. | Pass | NA
Neg_0005 | Image resizing | Upload a valid JPG image and enter the value 99999 into the width field while Keep aspect is ticked, then start the resize. | The tool should reject the extreme values or warn the user that the requested dimensions exceed the supported maximum. | The tool accepted the values, attempted to process the request and the browser tab became unresponsive without showing any limit warning. | Fail | It is assumed that the resizer should enforce an upper bound on dimensions and inform the user when the entered values are out of range.
Neg_0006 | Image resizing | Upload a valid PNG image, leave both the width and height input fields blank, and click the resize button. | The resize action should be blocked and a message should ask the user to provide both width and height values before proceeding. | The button click had no effect and no guidance was displayed to indicate that the empty fields were the cause. | Fail | It is assumed that empty dimension fields should trigger an inline validation message rather than a silent failure.
Pos_0003 | Image resizing | Upload a 1920x1080 PNG photograph and resize it to 800x450 px while keeping the aspect ratio locked. | A new image with the requested 800x450 dimensions should appear in the preview area. | The resized image was rendered at 800x450 in the preview and was available for download. | Pass | NA
Neg_0007 | Cropping | Upload a valid JPG image, then drag the crop selection box outside the boundaries of the image (beyond the visible edges) and apply the crop. | The crop selection should be constrained within the image area, or the tool should warn that the chosen region extends beyond the image and block the operation. | The selection was allowed to extend past the image edges and the resulting output contained large blank regions with no warning to the user. | Fail | It is assumed that the crop selector should be clipped to the image bounds so that only valid pixel data is included in the output.
Neg_0008 | Cropping | Upload a valid PNG image, manually type a negative value (such as -50) into the X-coordinate field of the crop region, and start the crop. | The coordinate field should refuse the negative input or the crop action should be halted with a message indicating that coordinates must be zero or positive. | The field accepted the negative number and the crop button initiated processing, ultimately returning an output that did not match the original image area. | Fail | It is assumed that crop coordinates should be validated against the image boundaries so that only non-negative values within the image are permitted.
Pos_0004 | Cropping | Upload a JPG, draw a freehand rectangular selection roughly in the centre of the image, and confirm the crop. | The cropped result should be displayed in the preview and exclude the area outside the selection. | The cropped output matched the drawn selection and was rendered correctly in the preview. | Pass | NA
Neg_0009 | Compression | Upload an extremely large image (approximately 60 MB) and start the compression. | The tool should warn that the file exceeds the maximum allowed size or stop the operation gracefully. | The page froze for several seconds and finally returned to its initial state without any message. | Fail | It is assumed that oversized files should be detected upfront with a clear size-limit warning.
Neg_0010 | Compression | Upload a valid JPG image, then drag the quality slider all the way down to 0% and run the compression. | The tool should either prevent the slider from reaching an unusable value or warn the user that compressing at 0% will destroy image content, and require a higher quality setting before proceeding. | The slider was accepted at 0%, compression ran to completion and produced an output that was almost entirely unreadable without any warning to the user. | Fail | It is assumed that the compressor should enforce a sensible minimum quality threshold or alert the user when the chosen setting would render the image unusable.
Pos_0005 | Compression | After uploading a JPG, move the quality slider from 80% to 40% and observe the preview. | The preview should refresh to reflect the lower quality and the estimated file size should drop. | The preview updated to a lower quality version and the displayed size decreased accordingly. | Pass | NA
Neg_0011 | Image format conversion | Upload an image whose internal data has been corrupted (renamed binary file with a .png extension). | The converter should detect the invalid image and display a read-error notice. | The converter loaded the file, attempted to convert it, and produced a broken output without warning. | Fail | It is assumed that the converter should validate image headers before attempting conversion.
Neg_0012 | Image format conversion | Upload a PNG image that contains a transparent background and convert it to JPG. | The converter should warn the user that JPG does not support transparency before proceeding, or it should apply a clearly stated fill colour to the transparent regions. | The conversion ran to completion without any warning, and the transparent regions in the resulting JPG were rendered as solid black, which was unexpected. | Fail | It is assumed that the converter should inform the user of format limitations such as the loss of transparency before producing the output, so that the result is not surprising.
Pos_0006 | Image format conversion | Upload a PNG and convert it to JPG using the default quality. | A JPG file with the same visible dimensions should be produced and offered for download. | A JPG version of the image was produced and the download button was made available. | Pass | NA
Neg_0013 | Meme generation | Type top and bottom text into the meme inputs without uploading any image, then click generate. | The tool should warn that an image must be uploaded before a meme can be created. | The generate button remained inactive but no helper text was displayed to the user. | Fail | It is assumed that the user should be told why the generate action is unavailable when no image is loaded.
Neg_0014 | Meme generation | Upload a valid PNG image and paste a very long string of text (around 500 characters) into the top text field, then generate the meme. | The tool should either limit the input to a reasonable character count or scale and wrap the text so that it remains readable within the image area. | The full text was rendered onto the image without wrapping or scaling, causing it to overflow beyond the image edges and become unreadable. | Fail | It is assumed that the meme generator should handle long captions gracefully through wrapping, scaling or a character limit, rather than allowing text to spill outside the image area.
Pos_0007 | Meme generation | Upload a PNG, type 'WHEN THE BUILD' as top text and 'FAILS AT 3 AM' as bottom text, then generate the meme. | Both lines of text should appear over the image in the standard meme font and remain readable. | Both captions appeared on the image in the expected position and font, and the result was downloadable. | Pass | NA
Neg_0015 | Color picker | Click the "Copy" button next to the Hex Code field after the page first loads, without changing the default selection. | A visible confirmation message or toast should appear indicating that the hex value has been copied to the clipboard. | The button responded to the click but no confirmation message or visual feedback was shown, leaving the user unsure whether the copy was successful. | Fail | It is assumed that any copy-to-clipboard action should display a brief confirmation so the user knows the operation completed.
Neg_0016 | Color picker | Click directly inside the Hex Code text "#000000" and attempt to type a different valid hex value (for example, FF5733) using the keyboard. | The interface should either accept the typed hex value and update the picker accordingly, or clearly indicate that the field is read-only and values can only be set through the picker controls. | The keyboard input had no effect on the Hex Code value and no message was displayed to indicate that direct entry was not supported. | Fail | It is assumed that the user should be able to either enter a hex code manually or be informed that direct editing is not supported.
Pos_0008 | Color picker | Drag the vertical hue slider on the right toward the red region, then drag the circular handle inside the gradient area to the top-right corner so a bright red is selected. | The Selected Color preview, the Hex Code value and the RGB value should all update simultaneously to reflect a bright red shade (approximately #FF0000 and rgb(255, 0, 0)). | The Selected Color preview turned bright red, the Hex Code updated to a value close to #FF0000 and the RGB display updated to rgb(255, 0, 0), all in sync with the handle position. | Pass | NA
Neg_0017 | Image rotation | Use the "Select files" button to upload a PNG image that is approximately 25 MB in size, which exceeds the 20 MB limit displayed beneath the upload area. | The upload should be refused immediately and a message should appear stating that the chosen file is larger than the maximum allowed size of 20 MB. | The upload appeared to begin, the page froze briefly, and then returned to its initial state without any message to indicate that the file exceeded the size limit. | Fail | It is assumed that files exceeding the documented 20 MB limit should be rejected upfront with a clear size-limit notification rather than failing silently.
Neg_0018 | Image rotation | Use the "Select files" button to upload a valid BMP image, which is outside the listed PNG, JPG and WEBP support shown beneath the upload area. | The tool should refuse the BMP file and display a message indicating that only PNG, JPG and WEBP formats are accepted, in line with the supported-format note. | The file was rejected but the message shown was a generic "invalid file" notice that did not specify which formats are actually permitted. | Fail | It is assumed that unsupported image formats should produce a message that explicitly lists the accepted formats so the user knows what to upload.
Pos_0009 | Image rotation | Upload a landscape-orientation JPG image through the "Select files" button, then click the "+90°" button once. | The Preview panel should refresh to display the same image rotated 90 degrees clockwise, with the width and height visually swapped relative to the original. | The preview updated immediately to show the image rotated 90 degrees clockwise, with the width and height correctly swapped. | Pass | NA
Neg_0019 | Image flipping | Use the "Select files" button to upload a GIF image, which is outside the listed PNG, JPG and WEBP support shown beneath the upload area. | The tool should refuse the GIF file and display a message indicating that only PNG, JPG and WEBP formats are accepted, in line with the supported-format note. | The file was rejected but no message was displayed near the upload area to indicate which formats are actually supported. | Fail | It is assumed that an unsupported image format should produce a message that explicitly lists the accepted formats so the user can correct the upload.
Neg_0020 | Image flipping | Upload a valid JPG image, then tick both the "Flip Horizontal" and "Flip Vertical" checkboxes simultaneously and click "Download PNG". | The Preview panel should reflect the combined effect of both flips and the resulting downloaded image should match the preview, or the tool should warn that only one flip can be applied at a time. | The preview applied only the horizontal flip while the vertical checkbox state was visually ignored, and the downloaded file matched the preview rather than reflecting both selections. | Fail | It is assumed that the tool should either apply both flips together or clearly indicate that the two options are mutually exclusive.
Pos_0010 | Image flipping | Upload a valid JPG image through the "Select files" button, then tick the "Flip Vertical" checkbox. | The Preview panel should refresh to display the same image flipped along its horizontal axis, so that the top and bottom of the original image appear swapped. | The preview updated immediately to show the image flipped vertically, with the original top and bottom correctly inverted. | Pass | NA
Pos_0011 | Document conversion | On the Word → PDF page, click the "Select Word" button, choose a valid .docx file, and then click "Convert to PDF". | The Selected panel should display the chosen file name together with its size, the "Convert to PDF" button should become available, and after clicking it a converted PDF version of the document should be produced for download. | The Selected panel correctly listed the file name and its size in KB, the Convert to PDF button became active as expected, and a PDF version of the document was produced and offered for download after clicking it. | Pass | NA
Pos_0012 | PDF editing | On the PDF Editor page, click "Choose File" and open a multi-page PDF document, then click the "Next" button in the Page section once. | The Toolbar should display the chosen file name next to the Choose File button, the page indicator should change from its initial state to show "1 / 8", and after clicking Next the indicator should advance to "2 / 8" while the canvas refreshes to display the second page of the document. | The file name appeared in the Toolbar as expected, the page indicator correctly showed "1 / 8" once the document loaded, and clicking Next advanced the indicator to "2 / 8" with the canvas refreshing to display the second page. | Pass | NA
Pos_0013 | Image resizing | On the Resize Image page, click "Select files" and upload a square PNG image (for example a 720x720 image), confirm that the "Keep aspect" checkbox is ticked, then change the value in the width field from 720 to 360 and observe the height field. | The Resize panel should display the original dimensions as "Original: 720x720", and when the width is changed to 360 the height field should automatically update to 360 to preserve the 1:1 aspect ratio, with the Download PNG button remaining available. | The original dimensions appeared as "Original: 720x720", changing the width to 360 caused the height field to auto-update to 360 as expected, and the Download PNG button stayed enabled throughout. | Pass | NA
Pos_0014 | Cropping | On the Crop PNG page, click "Select files" and upload a valid PNG image, then update the numeric crop fields to X=6, Y=1, Width=581 and Height=399, and observe the Preview panel. | The Crop panel should display the original dimensions as "Original: 600x400", the crop selection rectangle on the image should align with the entered X, Y, Width and Height values, and the Preview panel should refresh to render the area defined by those coordinates. | The original dimensions appeared as "Original: 600x400", the selection rectangle aligned with the entered X=6, Y=1, Width=581, Height=399 values, and the Preview panel rendered the corresponding cropped region as expected. | Pass | NA
Pos_0015 | Image format conversion | click "Select files" and upload a valid JPG image, confirm that the Format dropdown is set to "JPG → PNG", then click the "Download" button. | The Convert panel should display the source dimensions as "Size: 960x1280", the Preview panel should refresh to render the uploaded image in place of the "No image yet" placeholder, and clicking Download should produce a PNG version of the image for the user to save. | The Convert panel correctly listed the dimensions as "Size: 960x1280", the Preview panel rendered the uploaded image as expected, and clicking Download produced a PNG file with the same visible content as the source. | Pass | NA